## Work Items
Key | Summary | Description | Assignee | Remaining Estimate | Estimate w/Overhead | Estimate Notes | Fix Version/s
GMT-17 | GMT-3 Check in eclipse script test bugs |  | Joel Parker | 0 | 0 | Remove this task | (Removed)
GMT-16 | GMT-3 Run Script tests |  | Joel Parker | 0 | 0 | Remove this task | (Removed)
GMT-15 | GMT-3 Write eclipse script tests |  | Joel Parker | 7.75 | 9.3 | 23 tests/21 hours logged = ~1 hr per test; 62 tests rem. @ 1hr per test = 7.75 days | Someday
GMT-251 | GMT-3 Write GUI system test plan |  | Joel Parker | 0 | 0 | Remove this task | (Removed)
GMT-21 | GMT-3 Eclipse validation GUI tests |  | Shawn Hoffman | 0.5 | 0.6 |  | Someday
GMT-19 | GMT-3 EclipseLocator object script validation tests |  | Steven Hughes | 1.5 | 1.8 |  | Someday
GMT-252 | GMT-3 Write EclipseLocator interface spec |  | Steven Hughes | 0.5 | 0.6 |  | Someday
GMT-4 | GMT-3 Implement reporting requirements during solver processes |  | Darrel Conway | 3 | 3.6 | Assumed fixed, but 333 touches this part; 3 days to implement reporting only at solution | 2012a M3
GMT-335 | Mars Formation Eclipse Location Causes Crash | 14 Feb. 2012 build. Windows 7 Enterprise. This test has 6 spacecraft propagated at Mars in formation and attempts to locate all eclipses for all spacecraft. I see a crash upon build and run. | Darrel Conway | 2 | 2.4 | Issue here is formation handling | 2012a M3
GMT-255 | EclipseLocator is slow | The EclipseLocator tends to be slow. This bug is a placeholder to track performance-related issues. | Darrel Conway | 0 | 0 | Broken into smaller chunks | Someday
(new) | Add the derivative check discussed in e-mail |  | Darrel Conway | 3 | 3.6 | After each change, evaluate performance to see if the next step is needed | 2012a M3
(new) | Refactor local variables into class |  | Darrel Conway | 1 | 1.2 |  | Someday
(new) | Profile Event Location |  | Darrel Conway | 2 | 2.4 |  | Someday
(new) | Make changes based on profiling |  | Darrel Conway | 8 | 9.6 | timeboxed to total 14d | Someday
GMT-197 | Event locator fails to find eclipse after targeting | 18 Jan 2011 build. Windows 7 Enterprise | Darrel Conway | 1 | 1.2 | Related to GMT-333 | Someday
GMT-173 | Event Location conflicts with monotonic requirement for ephemeris file generation | During event location, the ephemeris file interpolator is being passed non-monotonic data if we are simultaneosly locating events. This issue does not occur during a stopping condition which is another iterative event location process that will have non-monontonic data. We need to use a similar process used to avoid this issue for stopping conditions. | Darrel Conway | 3 | 3.6 |  | Someday
GMT-334 | Eclipse Locator Fails during finite burn | 14 Feb. 2012 build. Windows 7 Enterprise There appears to be PropStateManager bookkeeping issue when performing finite burn and eclipse location simultaneously. I get this message when I run the attached script which attempts to locate eclipses during a finite burn. Propagator Exception: MassFlow is not a known propagation parameter on EclipseLocator1 | Darrel Conway | 2 | 2.4 |  | Someday
GMT-305 | Set up trial code review of event location code | Set up for moderation of the trial code review of event locator code. | Wendy Shoan |  | 0 |  | Someday
GMT-306 | Perform trial code review of event locator code | Suggested areas for review: EventModel or EventLocator. | Wendy Shoan |  | 0 |  | Someday
GMT-257 | GMT-3 Update design spec |  | Darrel Conway | 2 | 2.4 |  | 2012a M3
GMT-256 | GMT-3 Clean up code for review |  | Darrel Conway | 1 | 1.2 |  | Someday
GMT-261 | GMT-3 Write EclipseLocator Common Tasks sections |  | Joel Parker | 2 | 2.4 |  | Someday
GMT-262 | GMT-3 Write EclipseLocator reference page |  | Harvey Walden | 4 | 4.8 |  | Someday
GMT-259 | GMT-3 EclipseLocator code review | Estimate captures prep time (1d) + review time (5d) | Wendy Shoan | 6 | 7.2 |  | Someday
GMT-260 | GMT-3 Finalize EclipseLocator project docs |  | Joel Parker | 3 | 3.6 |  | Someday
GMT-258 | GMT-3 Write EclipseLocator reference text |  | Steven Hughes | 1 | 1.2 |  | Someday
GMT-372 | Need a test system comparator for FreeFlyer eclipse reports | The test system currently can only compare against STK eclipse reports, not those from FreeFlyer. This is necessary for antumbra tests (at least). | Joel Parker | 0 | 0 | remove this task; assumes a solution | (Removed)
GMT-371 | Antumbra function is not being tested | The antumbra event function is currently not being tested against truth data (only for crashes/errors). | Joel Parker | 5 | 6 | need to figure out a solution, then implement whatever it is | Someday
GMT-376 | Bad final step in eclipse location in For loop | Running the attached script in the 2012-02-24 build produces this error: {noformat} Integrator attempted too many steps! (51 attempts taken) Command Exception: In LocateEvent, Propagator prop failed to take a good final step (size = -9215.677976334700) {noformat} The script runs fine without the EclipseLocator, or with a single Propagate statement and no For loop. | Darrel Conway | 3 | 3.6 | probably the same as "Propagator hang during location" | Someday
GMT-377 | Error with eclipse detection in Mars trajectory | Not sure what a better title for this bug would be... When I run the attached case, I get this error once the propagation reaches Mars: {noformat} Event Exception Thrown: ERROR: The position vector, magnitude 6378.14, is inside of the occulting body (Earth, radius 6378.14) when calculating Penumbra {noformat} To get this far, I needed to set {{PropNearMars.MinStep = 0}}. Perhaps this is related, or maybe it's a different issue? Also, it sounds like this could be related to GMT-333, since it sounds like an origin issue. | Darrel Conway | 2 | 2.4 |  | Someday
GMT-378 | No eclipses located in Optimize | The attached script {{Events_Eclipse_LunarTransfer_Optimize.script}} does a lunar transfer inside an Optimize sequence. It runs successfully, but finds no eclipses. {{Events_Eclipse_LunarTransfer.script}} does the same transfer, but with hard-coded optimal values. This version finds the same eclipses as the truth data. | Darrel Conway | 2 | 2.4 | Related to GMT-333 | Someday
GMT-344 | Eclipse locator testing tolerance is too high | The tolerance on eclipse location tests with shadows from the spacecraft's central body is too high (5s). It should be more like 1s. | Joel Parker | 5 | 6 | depends on changing meaning of Tolerance | Someday
GMT-13 | Add tooltips to EclipseLocator panel |  | Steven Hughes | 0 | 0 | Remove this task | (Removed)
GMT-391 | Crash when SPK propagator generates an exception | The attached script and SPK file generate an exception without an EclipseLocator (due to GMT-390), but with the EclipseLocator, GMAT crashes. Tested with build 2012-02-28. | Darrel Conway | 2 | 2.4 |  | Someday
(new) | Reevaluate eclipse report format | There have been some change requests to the eclipse report format, such as rearranging columns. Also, some improvements may be warranted to make automatic parsing easier. | Joel Parker | 1 | 1.2 |  | Someday
(new) | Make requested eclipse report format changes |  | Darrel Conway | 1 | 1.2 | Assumes no data changes | Someday
(new) | EclipseLocator.Tolerance should be in units of seconds |  | Darrel Conway | 3 | 3.6 |  | Someday
(new) | Location during backprop |  | Darrel Conway | 3 | 3.6 |  | Someday
(new) | Propagator hang during location |  | Darrel Conway | 3 | 3.6 |  | Someday
(new) | Minstep issues |  | Darrel Conway | 0 | 0 | Needs more information | Someday

## Rollup
Row Labels | Sum of Estimate w/Overhead
2012a M3 | 12
Darrel Conway | 12
Someday | 89.1
Darrel Conway | 44.4
Harvey Walden | 4.8
Joel Parker | 28.5
Shawn Hoffman | 0.6
Steven Hughes | 3.6
Wendy Shoan | 7.2
(Removed) | 0
Joel Parker | 0
Steven Hughes | 0
Grand Total | 101.1