## SolarSystem
Solar System Work Items for the General Mission Analysis Tool (GMAT)
Phase When Estimated: May. 2009
|  | Bookkeep |  |  |  | Indiviual Prioritizations
Feature | Priority | Accepted | Best Case | Worst Case | Mean | LOJ | DJC | WCS | SPH | Owner | Comments
Solar System Related Work Items
Fix linking issue on PC | H |  | 3 | 4 | 3.5 | 3 |  |  | 4 | LOJ | I think LOJ said we need to recompile the SPK library on windows.
Fix GetMJ2000State for bodies | H |  | 3 | 3 | 3 |  |  | 3 | 3 | WCS | There is an issue when calling GetMJ2000State for the Sun, and perhaps for moons.
Create defaults for moons, asteriods, comets. | H |  | 1.5 | 1.5 | 1.5 |  |  |  | 1.5 | SPH | Develop default for moon, asteroid, and comet.
Define and implement allowable coordinate systems for body orientation definition | H |  | 0.5 | 1 | 0.75 |  |  | 1 | 0.5 | WCS | We need to decide which coordinate systems the user can use for defining celestial body orientation parameters.
Solar System Save only non default values | H |  | 3 | 4 | 3.5 |  |  | 3 | 4 | WCS | The solar system needs to save all user modified settings the script file when a user saves a mission.
Fix show script for celestial bodies to show only settable parameters. | H |  | 0.5 | 1 | 0.75 |  |  | 0.5 | 1 | WCS | The show script window should only show settable parameters for celestial bodies
Fix show script for solar system to show only solar system settable parameters | H |  | 0.5 | 1 | 0.75 |  |  | 0.5 | 1 | WCS | The show script window should only show settings specific to the solar system panel.
Develop math for attitude reference epoch and implement in code. | H |  | 1 | 1 | 1 |  |  |  | 1 | SPH | The attitude initial condition need to also have a reference epoch. We need to include math to handle this.
Add RotationDataSource to all default bodies | H |  | 2 | 2 | 2 |  |  |  | 2 | WCS | Set to IAU2002 for all bodies except moon and earth. Earth should have FK5_IAU1980 as the only option. Luna is good as is. This also means that orientation data should be greyed out for all default bodies.
Subtotal |  | 0 | 15 | 18.5 | 16.75 | 3 | 0 | 8 | 18
Title

## FiniteBurn
Burn Related Work Items for the General Mission Analysis Tool (GMAT)
Phase When Estimated: May. 2009
|  | Bookkeep |  |  |  | Indiviual Prioritizations
Feature | Priority | Accepted | Best Case | Worst Case | Mean | LOJ | DJC | WCS | SPH | Owner | Comments
Finite Burn Related Work Items
Fix coordinate system issue for thruster. | H |  | 5 | 5 | 5 |  |  |  | 5 | DJC | This is a state manager issue. The coordinate system needs to get the current state from the state vector and not from the spacecraft. Otherwise, the coordinate system is not updated at the integrator stages. This could be a more general problem when events are added.
Fix Mass depletion | H |  | 3 | 3 | 3 |  |  |  | 3 | DJC | Add mass as an integrator state
Review transient force mod for branch commands | [8 empty] | 0.5 | DJC | Finite burn was not working inside branch commands. Linda made a fix but requested that DJC review it.
Fix local coordinate system origin | H |  | 1 | 1.5 | 1.25 | 1.5 |  |  | 1 | LOJ | Currently base code uses primary as the origin for local maneuver coordinate systems. We need to use the spacecraft as the origin.
Add Group boxes to Thruster and Impulsive Burn GUI | H |  | 0.5 | 1 | 0.75 | 0.5 |  |  | 1 | LOJ | Add all coordinate system related data to "Coordinate System" group box. Add Element1, Element2, Element3, Duty Cycle, and, and Thrust Scale Factor to "Thrust Vector" group box. Add Decrement Mass, Tank, and Gravitational Accel to "Mass Change" group box.
Change Thruster Defaults | H |  | 0.5 | 1 | 0.75 | 0.5 |  |  | 1 | LOJ | Set C1 to 10. Set K1 to 300. All other values should be zero.
Subtotal |  | 0 | 10 | 11.5 | 10.75 | 2.5 | 0 | 0 | 11.5
Title